## Main
Screen / Function | Feature | Description | Role | LOC | Planned-In | In Charge | RDS | Status | Updated | Update Details | Trans | Quantity | Locs | Total
User Register | Register account | Check email if exist not register, User name at least 9 character, User name not space, password at least 9 and 1 uppercase 1 lowercase and not space and contain at least 1 special character | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 7 | 90 | 90 | 81
| verify otp | Check otp match | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
User Login | Login account | Check email if exist not login, check email if exist account GG not login, check email password match | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 7 | 90 | 90 | 81
| Login remember me | Storage cookie email , password fake | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Login google | Accsess token google then have infomation gmail google insert database | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  |  |  |  | 0
Homepage | View list categorys | View list categorys | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 9 | 90 | 120 | 108
| View list products | View list products | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View list new products | View list new products | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  |  |  |  | 0
| View list high price products | View list high price products | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View list high rating products | View list high rating products | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Add wishlist API | Add wishlist API by product id and userid | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Add cart API | Add cart API by product id and userid | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View List weights-price productdetails to select, Add compare product | View List weights-price productdetails to select by productid | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Search product api and search submit | Search product api and search submit | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Shop | View list information products | View list information products | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 10 | 90 | 150 | 135
| View category, View Rating | View category, View Rating | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Filter category, rating, range price, sort by | Filter category, rating, range price, sort by | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Delete filter | Delete filter (reset productid equal 0) | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Pagination list products | Use limit systax of mysql and each page 9 products and total records divided 9 products => total pages | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Add cart API | Add cart API by product id | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Click product link product details | Click product link product details | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View List weights-price productdetails to select | View List weights-price productdetails to select by productid | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Add compare product | Add compare product | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Add wishlist API | Add wishlist API by product id and userid | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Product detail | View list information products detail | View list information products detail include image, product name, rating, weight, price | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 9 | 90 | 120 | 108
| Choose quantity and add to cart | Validate quantity add to cart | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Add Comment product | Add Comment product | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View comment product | View list comment product | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Comment dislike, like API | Comment dislike, like API by comment productid | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Add wishlist | Add wishlist API by product id and userid | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Add compare | Add compare | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View list trending of products | View list trending of products | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View list Related of products | View list Related of products | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Cart | View list carts | View list carts | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 6 | 90 | 90 | 81
| Validate quantity API | Validate quantity API | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Delete cart | Delete cart | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View Total money and submit process checkout | View Total money and submit process checkout | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Checkout | Select address order | Select address order | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 6 | 90 | 90 |  | 930
| Add voucher | Add voucher | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Payment scanner QR to link PAYOS | Payment scanner QR to link PAYOS OCB BANK | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Payment deposit money to wallets | Payment deposit money to wallets | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View list carts and total money | View list carts and total money | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Order success And Order detail | View order and link Order details | View order and link Order details | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 6 | 90 | 90 | 81
| View list orders and total money | View list orders and total money | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Link invoice | Link invoice | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Review Order and update image (status completed) | Review Order and update image (status completed) | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Order Tracking | Order Tracking | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Order tracking | Search order code and link order detail to view order tracking | Search order code and link order detail to view order tracking | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Wishlist | View list products wishlist | View list products wishlist | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 3 | 50 | 60 | 30
| Delete 1 product wish list or Delete All Product wishlists | Delete 1 product wish list or Delete All Product wishlists | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Compare | View list products compare | View list products compare | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 6 | 70 | 90 | 63
| Delete 1 product compare | Delete 1 product compare | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Contact us | Submit form content of contact us | Submit form content of contact us | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
AI ChatBox | Call api by create API KEY google | Call api by create API KEY google | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 5 | 90 | 60 | 54
User profile | Deposit money into the wallet by PAYOS | Deposit money into the wallet by PAYOS | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done |  | 9 | 90 | 120 | 108
| View list orders | View list orders | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Change status orders | Change status orders | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| View comment product | View comment product | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| CRUD API address book | CRUD API address book | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Edit profile user | Edit profile user | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Change paasword(encode) | Change paasword(encode) | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
| Delete account(soft delete) | Delete account(soft delete) | User |  | Iteration 1 | AnhNH | Iteration 1 |  | Done
Seller Dashboard | Update Avatar | Allows sellers to upload a new profile picture. The image is cropped to a square shape, .webp files are rejected, and the file is saved with a fixed name. The newly uploaded avatar is instantly displayed without requiring a page reload. | Seller |  | Iteration 1 | ChienNX | Iteration 1 |  | d |  | 8 | 90 | 120 | 108
| Logout | Allows sellers to securely log out by clearing the current session and automatically redirecting them to the login page. | Seller |  | Iteration 1 | ChienNX | Iteration 1 |  | Done
| Enhanced Tab Navigation UX | Improves user experience with dashboard tab navigation, including retaining the active tab after reload and resetting data when switching tabs. | Seller |  | Iteration 1 | ChienNX | Iteration 1 |  | Done
Profile Tab | View & Edit Profile | Displays seller profile information including ID, Full Name, Email, Phone Number, Gender, Date of Birth, and Created Date. Allows editing with confirm/cancel options. | Seller |  | Iteration 1 | ChienNX | Iteration 1 |  | Done
| Change Password | Allows sellers to change their password using three input fields: current password, new password, and confirm new password. Passwords are encrypted using bcrypt. | Seller |  | Iteration 1 | ChienNX | Iteration 1 |  | Done
Product Tab | Manage Seller Products | Allows sellers to view, add, update, and soft delete products. Product creation includes validation for unique names, category selection, description input, status selection, and API integration. Updates auto-load existing data and validate name conflicts. Deletions mark products as INACTIVE. | Seller |  | Iteration 1 | ChienNX | Iteration 1 |  | Done |  | 18 | 90 | 200 | 180
| Manage Product Images | Provides image gallery management for each product, including viewing, zooming, uploading, and deleting images. Enforces a maximum of 5 images per product and synchronizes UI state across modal sessions without page reload. | Seller |  | Iteration 2 | ChienNX | Iteration 2 |  | Done | [5 empty] | 9.2727
| Enhanced Product List Interaction | Enables interactive list navigation with non-reloading pagination, product sorting by name/category (A–Z / Z–A), and auto-scroll/filtering when viewing product details. Pagination includes first/last page buttons and dynamic page ranges. | Seller |  | Iteration 2 | ChienNX | Iteration 2 |  | Done
Product Detail Tab | Manage Product Detail Records | Allows sellers to add, view, update, and soft delete product detail records. Each detail includes product name, weight–unit, price, expiry date, and status. Validates against duplicate weight–unit combinations within the same product. New records trigger pagination to the last page. | Seller |  | Iteration 2 | ChienNX | Iteration 2 |  | Done
| Filter and Navigate Product Details | Enables filtering the product detail list by selected product using a dropdown, and displays the list in either full or filtered mode. Pagination is applied on the client side without full-page reload, supporting smooth browsing of data. | Seller |  | Iteration 2 | ChienNX | Iteration 2 |  | Done
Order Tab | Order Management Interface | Provides a comprehensive UI for sellers to manage their orders, including order list display, API integration, pagination, keyword-based search (e.g. by Order ID, recipient name), and sortable columns like Order ID, Date, and Status. | Seller |  | Iteration 3 | ChienNX | Iteration 3 |  | Done |  | 16 | 90 | 180 | 162
| Manage Order Status & Tracking | Allows sellers to update the status of an order (Pending, Shipped, Cancelled, etc.) and view detailed order information, including products in the order and full status change history (tracking log). | Seller |  | Iteration 3 | ChienNX | Iteration 3 |  | To Do
Overview Tab | Business Overview Dashboard | Displays key business statistics for the seller, including total products, pending orders, revenue, sales charts (total revenue and trend), trending products, and recent orders. | Seller |  | Iteration 3 | ChienNX | Iteration 3 |  | To Do
Seller Become | Request to become a seller | Allows users to submit a request to become a seller and displays the current approval status (pending or approved) | User |  | Iteration 3 | ChienNX | Iteration 3 |  | To Do |  | 12 | 90 | 180 | 162
Blog List / Blog grid | Display blog pages for all users | All roles can view this, showing the 4 most recent posts ordered by createdAt, with pagination and search functionality for title and content | User |  | Iteration 1 | Đào Huy Hoàng | Iteration 1 |  | Done |  | 12 | 90 | 180 | 162
| Pagination support | Paginate blog posts with 5 records per page, with fixed first and last pages, and buttons for navigating to previous, next, and middle pages. | User |  | Iteration 1 | Đào Huy Hoàng | Iteration 3 |  | Done
| Product Trend Slider | As a user, when I browse the blog, I want to see trending products in the sidebar, and when I click any product, I am redirected to that product’s detail page. | User |  | Iteration 1 | Đào Huy Hoàng | Iteration 3 |  | Done
| Display blog pages for all users in a grid layout | All roles can view this, showing the 4 most recent posts ordered by createdAt, with pagination and search functionality. | User |  | Iteration 1 | Đào Huy Hoàng | Iteration 1 |  | Done
Blog Detail | Display detailed view of a blog, including image and related info | When a user clicks to view a specific blog from the list or grid, they are taken to a detailed page showing the complete blog content. | User |  | Iteration 1 | Đào Huy Hoàng | Iteration 1 |  | Done
| Comment Display | Show all comments for a specific blog post | User |  | Iteration 1 | Đào Huy Hoàng | Iteration 3 |  | Done
My Blog | Manage individual user blogs | Users can perform CRUD operations on their own blogs. Includes viewing, adding, editing, and deleting blogs. | User |  | Iteration 1 | Đào Huy Hoàng | Iteration 1 |  | Done |  | 9 | 90 | 120 | 108
| Open modal to add a new blog | Users can add blog details such as title, content, author, category (loaded dynamically from the database), status (Active, Inactive, Draft), and a thumbnail image. | User |  | Iteration 2 | Đào Huy Hoàng | Iteration 2 |  | Done
| Edit an existing blog | Users can edit their blog’s information, including title, content, author, and thumbnail image. | User |  | Iteration 2 | Đào Huy Hoàng | Iteration 2 |  | Done
| Soft delete a blog | Users can perform a soft delete on their blogs, which marks them as deleted without removing them permanently from the system. | User |  | Iteration 2 | Đào Huy Hoàng | Iteration 2 |  | Done
| Blog Dashboard - Total Blogs | Display total number of blogs submitted by the user in their My Blog dashboard. This feature helps users track the total number of posts they have published. | User |  | Iteration 2 | Đào Huy Hoàng | Iteration 3 |  | Done | [5 empty] | 428
| Display User Avatar | On My Blog dashboard, display the user’s profile picture (avatar) and allow the user to update their avatar. When the user logs in, their avatar will be visible. They can also upload a new avatar image | User |  | Iteration 2 | Đào Huy Hoàng | Iteration 3 |  | Done | [5 empty] | 66.3939
Blog Manager | CRUD operations for all blogs by Admin | Admin can perform CRUD operations on all user blogs with pagination and search functionality to manage the blogs of users. | Admin |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done |  | 9 | 90 | 120 | 108
| Filter by Status | Admin can filter all user blogs by status (ACTIVE, INACTIVE, DRAFT, DELETED) in the blog manager. Adds a dropdown/select box for status above the blog list. When a status is selected, only blogs matching that status are displayed. Includes “All” option to show all blogs regardless of status. | Admin |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| Pagination Support | Admin can paginate through user blogs with navigation options, ensuring easy management and viewing of blogs. Features include pagination with 5 records per page, fixed first/last pages, and navigation buttons for previous/next/middle pages. | Admin |  | Iteration 3 | Đào Huy Hoàng
| Search Functionality | Admin can search through all user blogs by title or content. This feature allows for quick and easy management of blogs by filtering and finding specific posts based on keywords. | Admin |  | Iteration 3 | Đào Huy Hoàng
Shipper Dashboard | Update Avatar | Allows shipper to upload a new profile picture. The image is cropped to a square shape, .webp files are rejected, and the file is saved with a fixed name. The newly uploaded avatar is instantly displayed without requiring a page reload. | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| Logout | Allows shipper to securely log out by clearing the current session and automatically redirecting them to the login page. | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| Enhanced Tab Navigation UX | Improves user experience with dashboard tab navigation, including retaining the active tab after reload and resetting data when switching tabs. | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
Profile Shipper | View & Edit Profile | Displays shipper profile information including ID, Full Name, Email, Phone Number, Gender, Date of Birth, and Created Date. Allows editing with confirm/cancel options. | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| Change Password | Allows shipper to change their password using three input fields: current password, new password, and confirm new password. Passwords are encrypted using bcrypt. | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
Shipper Doashboast | Display order status summary | Show number of orders with status STOCKOUT and DELIVERED + COMPLETED | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| Filter orders by status | Allows the shipper to filter orders by current status: ALL, PENDING, CONFIRMED, CANCELLED, STOCKOUT, DELIVERED, COMPLETED | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| Realtime Search | Enables shipper to instantly search orders by either phone number or order code with dynamic suggestions | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| Sort by Order Date | Allows the shipper to sort the order list by order date in ascending or descending order | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| Conditional Action Buttons | Displays “Mark as Delivered” (→ DELIVERED) and “Cancel Order” (→ CANCELLED) buttons only when status = STOCKOUT | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| Dynamic Pagination | Automatically splits the order list into multiple pages based on total records, with page navigation controls | Shipper |  | Iteration 3 | Đào Huy Hoàng | Iteration 3 |  | Done
| view addjustment of batch | View the list of inventory adjustments related to the batch, including adjustment quantity, type, reason, and timestamp. | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done
| search batch | Search batches by batch code, expiration date. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| sort batch | Sort displayed batch information as needed. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| Display expiration milestones | Display expiration milestones of each batch and automatically highlight rows based on progress: 50%, 70%, and 100% of shelf life to indicate approaching expiration. | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done
| Delete batch | Delete batches that have not been stocked in from the system. | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done
| pagination | Display data in pages for easier viewing and management. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
Add Product Batch | display list product detail | Display list of product details for selection when adding a new batch. | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done
| add productbatch | Add a new product batch to the system and automatically redirect to the batch list page upon successful addition. | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done
Supplier | display supplier | Display the list of suppliers in the system. | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done |  | 7 | 90 | 90 | 81
| sort supplier | Sort the supplier list by name | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done
| search supplier | search supplier by name | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| update supplier | Update supplier information with validate Name(only Vietnamese) and (Email valid format and phone 10 digit, each email or phone need unique) | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| delete supplier | Delete suppliers that have never stocked in before. | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done
| pagination | Display data in pages for easier viewing and management. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
Add Supplier | Add Supplier | Add a new supplier to the system and automatically redirect to the supplier list page upon successful addition. | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done
| Upload logo | Allows uploading a single logo file | Warehouse |  | Iteration 1 | QuangDN | Iteration 1 |  | Done
StockIn | display stockin | Display the list of stock-in records | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done |  | 7 | 80 | 90 | 72
| update stockin | Update stock-in information after validating the data. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
| sort StockIn | Sort stock-in records as needed. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| search StockIn | search by batchid, date stockin, note | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| view stockindetail | move to stockindetail | Warehouse |  | Iteration 2 | QuangDN | Iteration 3 |  | Done
| pagination | Display data in pages for easier viewing and management. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done | [5 empty] | 273
Add StockIn | Load information for add stockin | Load information for add stockin ( supplie , warehouse , batch avaiable) | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done | [5 empty] | 51.4545
| add stockindetail for stockin | Add detail information for the stock-in record. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
| add new batch for this stockin | Display detailed information of the stock-in record. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
StockIn Detail | stockindetail display | Display detailed information of the stock-in record. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done |  | 4 | 80 | 60 | 48
| load product img for stockin | Load product images for display in the stock-in record. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
| update stockindetail | update stockindetail | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
| calculate total import price | calculate total import price | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
Adjustment | Addjustment display | Display the list of inventory adjustments in the system. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done |  | 6 | 80 | 90 | 72
| update addjustment | Update inventory adjustment information after validation. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
| delete addjustment | Delete inventory adjustment from the system. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
| search addjustment | search addjustment by batch, reason, date, quantity | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| sort addjustment | Sort adjustment records by all displayed information. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| pagination | Display data in pages for easier viewing and management. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
StockOut | stockout display | Display the list of stock-out records in the system. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done |  | 7 | 80 | 90 | 72
| view stockout detail | move to sockout page and display | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
| search stockout | search stockout by ordercode , date , note | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| sort stockout | Sort stockout records by all displayed information. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| pagination | Display data in pages for easier viewing and management. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
StockOut Detail | stockoutdetail display | Display the list of stock-out detail records in the system. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| load product img for stockout | Load product images for display in the order record. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
Add StockOut | Display orders requesting stock-out | Display orders confirmed by the seller that require stock-out. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
| add stockout | Create stock-out records for orders that have requested dispatch. | Warehouse |  | Iteration 2 | QuangDN | Iteration 2 |  | Done
Return StockOut | show warehouse return requests | Show warehouse return requests submitted by delivery staff. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| access return stockout | access and changed status of stockout and update sold batch quantity | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
Warehouse Dashboard | show total stockin , stockout, batch , total expenditure | show total stockin , stockout, batch , total expenditure | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done |  | 12 | 90 | 180 | 162
| Show top 4 stockin, stockout most recent items by time. | Show top 4 most recent stock-in and stock-out records by time. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| Display recent system activities | Display recent system activities | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| to do list by day | to do list by day and access add job in day and it reset everyday | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
| Generate a chart showing total spending by month | Retrieve monthly spending data and generate a chart showing total spending for the latest 6 months. | Warehouse |  | Iteration 3 | QuangDN | Iteration 3 |  | Done
Admin Dashboard | Dashboard Overview | Show total number of products, orders, users, revenue, Revenue Report, top 3 best seller products, top 5 recent orders | Admin |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done |  | 9 | 90 | 120 | 108
Access Control | Authorization | Role-based access control, manage access permissions by screen and feature. |  |  | Iteration 2 | ThanhHV | Iteration 2 |  | Done
Category Management Page | View all categories | Display all categories in system. |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done |  | 9 | 90 | 120 | 90
| Edit category | Update category info such as : category name, describe, status. |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Search & Sort & Pagination & Filter | Allow admin to search category by name, ..and sort, filter and pagination |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Delete Category | Change category status to 'INACTIVE' , so all product will change to inactive. |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
Product Management Page | View all products | Display all products in system. |  |  | Iteration 1 | ThanhHV | Iteration 2 |  | Done |  | 8 | 90 | 120 | 108
| Edit product | Update product info such as : name, category, describe, status. |  |  | Iteration 1 | ThanhHV | Iteration 2 |  | Done
| Delete product | Change product status to 'INACTIVE' |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Export excel | Allow admin to export all data of product to new excel file. |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Search & Sort & Pagination & Filter | Allow admin to search product by name, ..and sort, filter product by category, status and pagination |  |  | Iteration 1 | ThanhHV | Iteration 2 |  | Done
Role Management Page | View all roles | Display all roles in system. |  |  | Iteration 1 | ThanhHV | Iteration 2 |  | Done |  | 9 | 100 | 120 | 120
| Edit role | Update role info: role name, describe |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Deactivate role | Change role status to "INACTIVE", all user has that role also "INACTIVE" |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done | [5 empty] | 900
| Search & Sort & Pagination & Filter | Allow admin to search role and sort each column in table, pagination, filter. |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Assign Role | Allows admin to assign a role to a user, defining their permissions and access within the system. |  |  | Iteration 2 | ThanhHV | Iteration 2 |  | Done
User Management Page | View all users | Display all users in system. |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done |  | 7 | 80 | 90 | 72
| View user information | Display information of selected user. |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Edit user information | Update user information: username, image, fullname, email, phone, address, role, Dob, Gender, Status, Image |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Search & Sort & Pagination | Allow admin to search user and sort columns. |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Delete user | Change user status to "INACTIVE" |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
Voucher Management Page | View all vouchers | Display all Vouchers in system include info: Voucher Code, DiscountType, DiscountValue, MinOrderValue, Status, ExpiryDate |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done |  | 7 | 100 | 90 | 90
| Create new voucher | Allows admin to add new voucher include voucher code, StartDate, EndDate, Type, Discount Value, Min Order Value, Quantity. |  |  | Iteration 2 | ThanhHV | Iteration 2 |  | Done
| Edit Voucher | Update voucher info: voucher code, StartDate, EndDate, Type, Discount Value, Min Order Value, Quantity. |  |  | Iteration 2 | ThanhHV | Iteration 2 |  | Done
| Search & Sort & Filter & Pagination & Export Excel | Allow admin to search voucher and sort columns, pagination, export data to excel |  |  | Iteration 2 | ThanhHV | Iteration 2 |  | Done
| Delete Voucher | If voucher has apply for any orders, voucher will be locked. Else voucher will be delete. |  |  | Iteration 2 | ThanhHV | Iteration 2 |  | Done
Order Management Page | View all orders | Display all orders in system. |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done |  | 10 | 80 | 150 | 120
| Edit status orders | Allows admin to update the status of orders (e.g., Pending, Confirmed, Delivered). |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done
| Search & Sort & Filter & Pagination & Export Excel | Allow admin to search order and sort columns, pagination, export data to excel |  |  | Iteration 1 | ThanhHV | Iteration 1 |  | Done
| Delete order | Change order status to "CANCELLED" if order status before is "PENDING" or "CONFIRMED" |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done
Order Tracking Page | Search by OrderCode | Allows admin to search for an order using its unique order code. |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done
| Order Tracking Detail | Displays the order information and current status of an order. |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done
Order Detail Page | View order detail | Display the details list of each order. |  |  | Iteration 2 | ThanhHV | Iteration 2 |  | Done
Forgot Password Page | Forgot Password | Allows users to initiate password recovery by entering their registered email. |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done |  | 8 | 100 | 120 | 120
OTP Page | Email OTP Verify | Sends a one-time password (OTP) to the user's email for verification. |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done
Profile Management | View & Edit Profile | Allows admin to view and update their personal profile information. |  |  | Iteration 2 | ThanhHV | Iteration 3 |  | Done |  | 6 | 80 | 90 | 72
Change Password Page | Change Password && Reset Password | Allows users to securely change their current password.Validate password at least 9 character, User name not space, password at least 9 and 1 uppercase 1 lowercase and not space and contain at least 1 special character |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done
Notification Panel | View recent notifications | Allow the admin to view the 10 most recent notifications, including the title, content, and timestamp. |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done
Notification System | Receive order placement alerts. Receive seller application alerts. | Automatically notifies the admin when a user places a new order successfully and user send seller-become request. |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done
Seller Application Management | View and process seller requests | Allows the admin to view user requests to become sellers and either approve or reject each request. |  |  | Iteration 3 | ThanhHV | Iteration 3 |  | Done